## Project information
Project name
A web application: Library management System
Description
Build a web application for Greenwich University to manage borrowing books. The application should allow: +The application should +Librarian: author management, book information management, member management, book return management +Members: register for a clean loan online
Team |  | Code
Liam Parker | Technical leader, Database designer, Developer | T003
Sophia Chen | Scrum Master,Tester, Developer | T004
Daniel Rodriguez | Developer | T005
Olivia Smith | Developer | T006

## Product Backlog
Item ID | Items | Priority | Sprint (1-6) | Start date | Finish date | Status | Story point | Assigned to sprint (Y/N)
Functional Requirements
1 | As an unauthorized User I want to login | High | 1 |  |  |  | 1
2 | As an authorized User I want to logout | High | 1 |  |  |  | 1
3 | As an authorized User I want to register an account | High
4 | As a librarian, I want to manage author information to easily add, edit, and view the author database. | High | 1 |  |  |  | 5
5 | As a librarian, I want to manage book information, allowing me to add, edit, and view the book database and link them to author information. | High | 2 |  |  |  | 8
6 | As a librarian, I want to manage member information, making it easy to add, edit, and view the member database. | High | 2 |  |  |  | 5
7 | As a librarian, I want to manage the book lending process, including information about borrowed books, lending dates, and return dates. | High | 3 |  |  |  | 8
8 | As a member, I want to register and borrow books online for convenience and efficiency. | High | 3 |  |  |  | 8
9 | As a librarian, I want a user-friendly interface for smooth interaction with the system. | Medium | 4 |  |  |  | 5
10 | As a member, I want the ability to manage personal information, including login, registration, and updating my personal details. | Medium | 4 |  |  |  | 5
Reporting
11 | As a librarian, I want the ability to create and view statistical reports on the number of books, members, and the book lending process to efficiently manage the library. | Medium | 5 |  |  |  | 5
12 | As a member, I want to receive a periodic email about new books | Low | 6 |  |  |  | 5
Non-Functional Requirements
13 | As a system administrator, I want the password of each account should be at least 8 characters with at least one upper letter | Medium | 1 |  |  |  | 1
14 | As a system administrator, I want the login step avoid SQL injection | Medium | 1 |  |  |  | 1
15 | As a Product owner, I want to use php, mysql technology | High | 1
16 | As a Product owner, I want to design the application with a responsive layout | High | 1

## Sprint1
Sprint goal: | Make the application run on Php, Mysql with responsive design layout
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 134 | 32 | 32 | 16 | 20 | 32 | 132
1 | As an unauthorized User I want to login | Design and modify database | T003 | 16 | 8 | 8 |  |  |  | 16
|  | Design login page layout | T006 | 3 |  |  | 3 |  |  | 3
|  | Code the login page layout | T006 | 4 |  |  |  | 4 |  | 4
|  | Write automated acceptance tests | T004 | 8 | 8 |  |  |  |  | 8
2 | As an authorized User I want to logout | Make logout function | T003 | 2 |  |  |  | 2 |  | 2
3 | As an authorized User I want to register an account | Design registration page | T006 | 5 |  |  | 5 |  |  | 5
|  | Code the registration page | T006 | 6 |  |  |  | 4 |  | 4
13 | As a system administrator, I want the password of each account should be at least 8 characters with at least one upper letter | Check the password when user create an account. Enforce the rule | T006 | 1 |  |  |  | 1 |  | 1
14 | As a system administrator, I want the login step avoid SQL injection | Applied techniques to avoid sql injection | T006 | 1 |  |  |  | 1 |  | 1
15 | As a Product owner, I want to use php, mysql technology | Set up the development enviroment | T004 | 8 |  | 8 |  |  |  | 8
16 | As a Product owner, I want to design the application with a responsive layout | Design overal structure of the application: page layout, menus, header footer…. | T006, T005 | 32 | 16 | 16 |  |  |  | 32
|  | Code the main theme of the application: page layout, menus, header footer…. | T005 | 16 |  |  | 8 | 8 |  | 16
|  | Do the unit testing | T003, T006, T005,T004 | 32 |  |  |  |  | 32 | 32

## Sprint2
Sprint goal:
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 24 | 0 | 0 | 8 | 0 | 0 | 8
4 | As a librarian, I want to manage author information to easily add, edit, and view the author database. | Design and modify database | T003 | 8 |  |  | 8 |  |  | 8
|  | Design and code author management page in which list all author in the database | T006, T005 | 3 | [5 empty] | 0
|  | Design and code add author popup form | T006, T005 | 4 | [5 empty] | 0
|  | Design and code edit author popup form | T006, T005 | 4 | [5 empty] | 0
|  | Design and code delete author function | T006, T005 | 3 | [5 empty] | 0
|  | Write automated acceptance tests | T004 | 2 | [5 empty] | 0

## Sprint3
Sprint goal:
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint4
Sprint goal:
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint5
Sprint goal:
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint6
Sprint goal:
Start date:
End date: |  |  |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Backlog ID | Backlog Item | Sprint task | Volunteer | Estimate effort hours | Mon | Tues | Wed | Thur | Fri | Total
Total estimate effort hours |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Minutes V1
Meeting No | Date | Minutes of meeting | What was discussed | Tasks Achieved: | Member present:
1 | 2024-01-15 | 140 | 1. Discussed technologies to use 2. Github tutorial 3.Created User Stories | 1. Choose PHP, Mysql, boostrap 2. Create github 3. Finish all user stories | Liam Parker, Sophia Chen, Daniel Rodriguez, Olivia Smith
2 | 2024-01-16 | 60 | 1. Broke down user stories to tasks 2. Prioritsed tasks in backlog 3. Assigned tasks to team members | 1. Finish product backlog with priority 2. Plan all 6 sprints 3. Assigned tasks to team members | Liam Parker, Sophia Chen, Daniel Rodriguez, Olivia Smith

## Minutes V2
Meeting No | 1
Date | 2024-01-15
Member present: | Liam Parker, Sophia Chen, Daniel Rodriguez, Olivia Smith
Minutes of meeting: | 140 minutes
What was discussed | 1. Discussed technologies to use 2. Github tutorial 3.Created User Stories
Tasks Achieved: | 1. Discussed technologies to use 2. Github tutorial 3.Created User Stories 4.Stated assumtions from specification
Meeting No | 2
Date | 2024-01-16
Member present: | Liam Parker, Sophia Chen, Daniel Rodriguez, Olivia Smith
Minutes of meeting: | 140 minutes
What was discussed | 1. Broke down user stories to tasks 2. Prioritsed tasks in backlog 3. Assigned tasks to team members
Tasks Achieved: | 1. Broke down user stories to tasks 2. Prioritsed tasks in backlog 3. Assigned tasks to team members